## Defect Report
Defect Id. | Module name | Defect Summary | Defect Priority | Assigned To | Status
To do
To do
To do
To do
To do
To do
To do
To do

## Test Cases- Sakshi
Test Case ID | Test Scenario | Precondition | Test Condition | Test Case Steps | Test Data | Expected Result | Actual Result Iteration 1 | Status Iteration 1 | Actual Result Iteration 2 (to be updated only if test case failed in Iteration 1) | Status Iteration 2 (to be updated only if test case failed in Iteration 1) | Comments | Req: Reference
<Sequence number> | <Identify test scenarios> | <This cell specifies the state a system and its environment must be in before this specific test case can be run> | <This cell describes what to test for i.e. the condition which is being tested for> | <This cell describes how to test i.e. the detailed testing procedure> | <Mention test data to be used> | <Describe the expected test result> | <Describe the actual test result after execution of test cases. In case screenshots need to be attached to substantiate the test result, use the references tab.> | Status of the test case whether it got passed/ failed/Hold in interation 1. | <Describe the actual test result after execution of test cases second time. In case screenshots need to be attached to substantiate the test result, use the references tab.> | New status of test case after it failed in Iteration 1.
TC_Navigation_01 | TS_Navigation_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page | To validate if the buttons in the navigation section are working and lead to relevant pages. | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Hover on all the 5 options (i.e paints & textures, wallpapers, services, ideas and shop) 4. A drop down menu should appear 5. Click all the 5 buttons one at a time (i.e paints & textures, wallpapers, services, ideas and shop) | https://www.asianpaints.com/ | User should be able to see the elements under each option after hovering and should be redirected to their specific pages. | User is able to hover over all the options. After clicking on the buttons, all of them work except "Ideas" button and is not redirected to any page. | Failed
TC_Navigation_02 | TS_Navigation_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page | To validate that the navigation section should have a working "Design and Colour App" tab. | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Click on "Design and Colour" button 4. Download app by clicking on "Get it on Google play" or "Download on Appstore" 5. Enter you mobile number to get the link of the app | https://www.asianpaints.com/ | User should be able to see the new redirected page properly and download the app. | User is able to view the page correctly and download the app. | Passed
TC_Navigation_03 | TS_Navigation_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page | To validate that the navigation section should have a working "Find a Contractor" tab. | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Click on "Find a Contractor" button 4. Type your pincode or city 5. Click on Search button | https://www.asianpaints.com/ | User should be able to see the new redirected page properly and find contractors | User is able to view the page correctly and find contractors | Passed
TC_Navigation_04 | TS_Navigation_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page | To validate that the navigation section should have a working "Find a Store" tab. | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Click on "Find a Store" button 4. Type your pincode 5. Click on Search button 6. Click on Book an appointment, enter your details and submit 7. Click on the blogs to view them | https://www.asianpaints.com/ | User should be able to see the new redirected page properly and find stores nearby. User should also be able to book an appointment and view any blog | User is able to view the page correctly, find stores, book an appointment and view blogs | Passed
TC_Navigation_05 | TS_Navigation_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page | To validate that the navigation section should have a toll free number. | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Click on the toll free number 4. Select an app with which you want to open it in 5. Call the number | https://www.asianpaints.com/ | User should be able to click on the number and call it with the app chosen | User is able to click on the number and call it | Passed
TC_Navigation_06 | TS_Navigation_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page | To validate that the navigation section should have a working "Home owners" drop down menu. | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Click on "Homeowners" button 4. In the dropdown menu, select any option | https://www.asianpaints.com/ | User should be able to see the dropdown menu and navigated to another page after selecting an option | User is able to see the options under dropdown menu and select any of them to view more information on another page | Passed
TC_Navigation_07 | TS_Navigation_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page | To validate that the navigation section should have a working "Wishlist" option. | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Click on "Wishlist" button 4. Go to shop, select wallstickers (or any other option) and add any product to the wishlist 5. Go to wishlist and click on the "X" mark to delete any item | https://www.asianpaints.com/ | User should be able to view the wishlist, add and delete items from wishlist | User is able to view the wishlish, add and delete any items from wishlist | Passed
TC_Navigation_08 | TS_Navigation_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page | To validate that the navigation section should have a working "Profile" option. | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Click on "profile" button 4. Enter your mobile number and OTP received to login 5. Click on "my profile" to navigate 6. Click on "signout" to logout from the account | https://www.asianpaints.com/ | User should be able to click on "profile" button and view "my profile" in another page. User should also be able to click on "signout" anytime required. | User is able to click on "profile", view "my profile" in another page and signout anytime. | Passed
TC_Navigation_09 | TS_Navigation_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page | To validate that the navigation section should have a working "View Cart" option. | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Click on "Cart" button to view items 4. Click on shop and go to wallstickers 5. Add any item in the cart | https://www.asianpaints.com/ | User should be able to add any item in the cart and view all of them | User is able to add any item to the cart and view all the items | Passed
TC_Navigation_10 | TS_Navigation_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to view the search bar | To validate if the "Search" bar is working. | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Click on the search bar 4. Type wall stickers/wallpapers (any product) | https://www.asianpaints.com/ | User should be able to search for all the products | User is able to search for all the products | Passed
TC_Login_01 | TS_Login_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to click on "profile" button 4. User is able to enter details (mobile number) | To validate if the user is able to login using valid credentials (valid mobile number and OTP). | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Click on "profile" button 4. Enter your mobile number and OTP received 5. Click Submit | https://www.asianpaints.com/ | User should be able to login | User is able to login | Passed
TC_Login_02 | TS_Login_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to click on "profile" button 4. User is able to enter details (mobile number) | To validate if the user is able to login using invalid credentials (invalid mobile number and invalid OTP) | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Click on "profile" button 4. Enter invalid mobile number and invalid OTP 5. Click Submit | https://www.asianpaints.com/ | User should not be able to login and a warning message should be shown | User cannot login and warning message "phone number is invalid" is shown | Passed
TC_Login_03 | TS_Login_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to click on "profile" button 4. User is able to enter details (mobile number) | To validate if the user is able to login using invalid mobile number and valid OTP | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Click on "profile" button 4. Enter invalid mobile number and valid OTP | https://www.asianpaints.com/ | User should not get the option of entering OTP as the mobile number is invalid and warning message "phone number is invalid" is shown | User gets a warning message "phone number is invalid" and is unable to enter OTP | Passed
TC_Login_04 | TS_Login_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to click on "profile" button 4. User is able to enter details (mobile number) | To validate if the user is able to login using valid mobile number and invalid OTP | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Click on "profile" button 4. Enter valid mobile number and invalid OTP 5. Click Submit | https://www.asianpaints.com/ | User should not be able to login and a warning message "invalid or expired OTP, please try again!" should be shown | User is unable to login and a warning message "invalid or expired OTP, please try again!" is shown | Passed
TC_Login_05 | TS_Login_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to click on "profile" button | To validate if the user is able to login without any credentials | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Click on "profile" button 4. Without entering mobile number, click sumbit | https://www.asianpaints.com/ | User should not get the option of entering OTP as the mobile number is invalid and warning message "field required" is shown | User gets a warning message "field required" and is unable to enter OTP | Passed
TC_Login_06 | TS_Login_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to click on "profile" button 4. User is able to enter details (mobile number and OTP) | To validate that after the user has logged in and browsing back using browser back button | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Click on "profile" button 4. Enter valid mobile number and valid OTP 5. Click Submit 6. Click the back button on browser | https://www.asianpaints.com/ | User should still be logged in | User remains logged in | Passed
TC_Login_07 | TS_Login_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to click on "profile" button 4. User is able to enter details (mobile number and OTP) 5. User is able to access all components on the website | To validate the timeout of the login session. | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) | https://www.asianpaints.com/ | User should automatically logout after a certain period of time | User is still logged in | Failed
TC_Login_08 | TS_Login_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to click on "profile" button 4. User is able to enter details (mobile number) | To validate if "terms and conditions" page is opening before user types OTP | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Click on "profile" button 4. Enter valid mobile number and submit 5. Click on "terms and condition" | https://www.asianpaints.com/ | User should be able to see the terms and condition | User is taken to homepage | Failed
TC_Tools_01 | TS_Tools_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to scroll down | To validate if the user is able to click on all the options | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Scroll down to the bottom of the page 4. Click on all the option under tools one at a time | https://www.asianpaints.com/ | User should be able to click on the buttons | User is able to click on the buttons | Passed
TC_Tools_02 | TS_Tools_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to scroll down | To validate if the user is navigated to specific pages after clicking on each button | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Scroll down to the bottom of the page 4. Click on all the option under tools one at a time | https://www.asianpaints.com/ | User should be navigated to another page and get more information about the topics | User is navigated to other page for all options except "Colour Academy". User is landing back to the homepage. | Failed
TC_StoreLocator_01 | TS_StoreLocator_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to scroll down and look for "Explore the Stores" | To validate that "AP Beautiful Homes", "Colour Ideas", "Signature Stores" buttons work and navigates user to pages with more information about it | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Scroll down to the bottom of the page 4. Click on all the option under tools one at a time | https://www.asianpaints.com/ | User should be navigated to another page and get more information about the topics | User is redirected to other page and is able to get more information | Passed
TC_StoreLocator_02 | TS_StoreLocator_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to scroll down and look for "Explore the Stores" | To validate that the user can enter pincode and click go button | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Scroll down and look for "Explore our Stores" 4. Enter pincode and click go button | https://www.asianpaints.com/ | User should be able to enter the pincode and click on go button to be redirected to another page | User is able to enter pincode and click go button. User is redirected to a page with more information about the dealers | Passed
TC_StoreLoactor_03 | TS_StoreLocator_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to scroll down and look for "Explore the Stores" | To validate if user is able to go ahead without entering any pincode | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Scroll down and look for "Explore our Stores" 4. Without entering pincode and click go button | https://www.asianpaints.com/ | User should get a warning message "Field Required" | User is getting a warning message "Field Required" and not able to proceed further | Passed
TC_StoreLocator_04 | TS_StoreLocator_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to scroll down and look for "Explore the Stores" | To validate if user is redirected to another page after typing a pincode | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Scroll down and look for "Explore our Stores" 4. Enter pincode and click go button | https://www.asianpaints.com/ | User should be redirected to another page | User is redirected to other page and is able to get more information | Passed
TC_StoreLocator_05 | TS_StoreLocator_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to scroll down and look for "Explore the Stores" | To validate if user is able to find any stores with invalid pincode | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Scroll down and look for "Explore our Stores" 4. Enter invalid pincode and click go button | https://www.asianpaints.com/ | User should not get any results | User is able to type invalid pincode without any warning message, but does not find any results | Passed
TC-StoreLocator_06 | TS_StoreLocator_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to scroll down and look for "Explore the Stores" | To validate if user is able to check the location on Google maps | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Scroll down and look for "Explore our Stores" 4. Enter pincode and click go button 5. Click on the button that will show the directions to the store | https://www.asianpaints.com/ | User should be redirected to a Google maps page with the directions to the store | User is redirected to a Google maps page that has the directions to the store | Passed
TC-StoreLocator_07 | TS_StoreLocator_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to scroll down and look for "Explore the Stores" | To validate if user is able to enter mobile number and email for getting information about the dealer | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Scroll down and look for "Explore our Stores" 4. Enter pincode and click go button 5. Click on the button that will give you an option to receive details via SMS or EMAIL | https://www.asianpaints.com/ | User should get a warning message for invalid and no credentials | User gets a warning message for invalid and no credentials | Passed
TC_Enquiry_01 | TS_Enquiry_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to scroll down and look for "Enquire now" option | To Validate if the user is able to enter valid credentials | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Scroll down and look for "Enquire Now" 4. Enter name, email, mobile number and pincode 5. Click "Enquire now" | https://www.asianpaints.com/ | User should get a "Thank You" message and should be able to download "Asian Paints Colour Book" | User gets a "Thank You" message and is able to download "Asian Paints Colour Book" | Passed
TC_Enquiry_02 | TS_Enquiry_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to scroll down and look for "Enquire now" option | To validate if the user is able to enter invalid credentials and enquire | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Scroll down and look for "Enquire Now" 4. Enter invalid name, invalid email, invalid mobile number and invalid pincode 5. Click "Enquire now" | https://www.asianpaints.com/ | User should get a warning message for invalid credentials | User is getting a warning message for invalid name, invalid email id, invalid phone number, but not for invalid pincode | Failed
TC_Enquiry_03 | TS_Enquiry_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to scroll down and look for "Enquire now" option | To validate if the user is able to enquire without providing any credentials | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Scroll down and look for "Enquire Now" 4. Without entering any credentials, click on "Enquire Now" | https://www.asianpaints.com/ | User should get a warning message "Field Required" | User is getting a warning message "Field Required" and not able to proceed further | Passed
TC_Shop_01 | TS_Shop_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to scroll down and look for "Shop Online" | To validate if the user is able to view suggested products on the homepage | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Scroll down and look for "Shop Online" | https://www.asianpaints.com/ | User should be able to see few general products in the suggestions | User is able to see few general products in the suggestions | Passed
TC_Shop_02 | TS_Shop_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to scroll down and look for "Shop Online" | To validate if the user is navigated to shop page after clicking on "View all" | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Scroll down and look for "Shop Online" 4. Click on "View all" | https://www.asianpaints.com/ | User should be redirected to the "Shop" page | User is redirected to "Shop" page | Passed
TC_MobileApp_01 | TS_MobileApp_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to scroll down and look for "Design and Colour App" | To validate if user is able to download app on Appstore and Playstore | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Scroll down and look for "Design and Colour App" 4. Click on "Download on Appstore" and "Get it on Playstore" | https://www.asianpaints.com/ | User should be redirected to another page where user can download the app | User is redirected to another page where user can download the app | Passed
TC_MobileApp_02 | TS_MobileApp_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to scroll down and look for "Design and Colour App" | To validate if the user is able to enter mobile number to get link to the app through SMS | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Scroll down and look for "Design and Colour App" 4. Enter your valid mobile number and click on "get link" | https://www.asianpaints.com/ | User should get an alert message "Message has been successfully sent to" | User is getting an alert message "Message has been successfully sent to" | Passed
TC_MobileApp_03 | TS_MobileApp_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to scroll down and look for "Design and Colour App" | To validate if "get link" button is working | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Scroll down and look for "Design and Colour App" 4. Enter your valid mobile number and click on "get link" | https://www.asianpaints.com/ | User should be able to click on get link and request for the link multiple times | User is only able to get link once on one mobile number. The "get link" does not work after using it once | Failed
TC_About&Policies_01 | TS_About&Policies_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to scroll down and look for "About" at the botton of the page | To validate if user is able to click on all the options available and gets redirected to other page | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Scroll down and look for "About" at the bottom of the page 4. Click on all the options to see if you are redirected to another page | https://www.asianpaints.com/ | User should be redirected to another page after choosing any option | User is redirected to another page after choosing any option | Passed
TC_About&Policies_02 | TS_About&Policies_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to scroll down and look for "About" at the botton of the page | To validate if user is able to enter details under warranty claim | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Scroll down and look for "About" at the bottom of the page 4. Click on the warranty option | https://www.asianpaints.com/ | User should be able to enter details in the warranty section | User is able to enter details in the warranty section | Passed
TC_About&Policies_03 | TS_About&Policies_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page 3. User is able to scroll down and look for "About" at the botton of the page | To validate if user are able to enter invalid details under warranty claim | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Scroll down and look for "About" at the bottom of the page 4. Click on the warranty option 5. Enter invalid details | https://www.asianpaints.com/ | User should get a warning message and not be able to proceed further | User is able to enter invalid details under mobile number, city, pincode and is able to proceed further without getting any warning message | Failed
TC_InteriorDesign_01 | TS_InteriorDesign_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page | To validate if user is able to view few examples of Interior design services | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Scroll down and look for "Interior Design Services" | https://www.asianpaints.com/ | User should be able to see the examples | User is able to see the examples | Passed
TC_InteriorDesign_02 | TS_InteriorDesign_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page | To validate if user is able to click on "book an appointment" | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Scroll down and look for "Interior Design Services" 4. Click on "Book an appointment" button | https://www.asianpaints.com/ | User should be able to click on "book an appointment" number and get redirected to other page | User is able to click on "book an appointment" number and gets redirected to other page | Passed
TC_InteriorDesign_03 | TS_InteriorDesign_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page | To validate if user is able to book an appointent with valid credentials | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Scroll down and look for "Interior Design Services" 4. Click on "Book an appointment" button 5. Enter your details | https://www.asianpaints.com/ | User should be able to enter the details and book an appointment | User is able to enter the details and book an appointment | Passed
TC_InteriorDesign_04 | TS_InteriorDesign_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page | To validate if user is able to book an appointment with invalid credentials | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Scroll down and look for "Interior Design Services" 4. Click on "Book an appointment" button 5. Enter invalid credentials | https://www.asianpaints.com/ | User should get a warning message for entering invalid credentials | User does not get a warning message for entering invalid pincode | Failed
TC_InteriorDesign_05 | TS_InteriorDesign_01 | 1. User is able to enter the URL and open the website 2. User is able to view the home page | To validate if user is able to book an appointment without providing any credentials | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) 3. Scroll down and look for "Interior Design Services" 4. Click on "Book an appointment" button 5. Without entering any details, proceed further | https://www.asianpaints.com/ | User should get a warning message "Field Required" | User gets a warning message "field required" | Passed

## Test Cases- Yogesh
Test Case ID | Test Scenario | Precondition | Test Condition | Test Case Steps | Test Data | Expected Result | Actual Result Iteration 1 | Status Iteration 1
<Sequence number> | <Identify test scenarios> | <This cell specifies the state a system and its environment must be in before this specific test case can be run> | <This cell describes what to test for i.e. the condition which is being tested for> | <This cell describes how to test i.e. the detailed testing procedure> | <Mention test data to be used> | <Describe the expected test result> | <Describe the actual test result after execution of test cases. In case screenshots need to be attached to substantiate the test result, use the references tab.> | Status of the test case whether it got passed/ failed/Hold in interation 1.
TC_P&T_PaintSelection_01 | TS_P&T_PaintSelection_01 | 1. User is able to successfuly land on Paints and Textures Page. | 1. To verify whether Paint Selection section is present or not. 2. To Verify if all the four Elements in this section are clickable or not. 3. To verify whether the user lands on correct pages after clicking the links. | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/products/paints-and-textures.html) 3. Locate Paint Selection section. 4. Check all the elements are clickable in this. 5. Check whether correct page is displayed upon clicking the elements | https://www.asianpaints.com/products/paints-and-textures.html | User should be able to see the Paint Selection Section and land on correct pages upon clicking. | User is able to see the Paint Selection Section and land on correct pages upon clicking. | Passed
TC_P&T_Wall/Paint_Ideas_01 | TS_P&T_Wall/Paint_Ideas | 1. User is able to successfuly land on Paints and Textures page | 1. To verify whether "Explore Ideas" page is working | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/resources/tools/paint-selector.html). 3. Click VIEW ALL IDEAS icon. | https://www.asianpaints.com/products/paints-and-textures.html | User should be able to see the Explore Ideas Section and land on correct pages upon clicking. | User is able to see the Paint Selection Section and land on correct pages upon clicking. | Passed
TC_P&T_Interior_Design_Services | TS_P&T_Interior_Design_Services | 1. User is able to successfuly land on Paints and Textures Page. | 1. To verify whether the Interior design Section is correctly displayed or not. 2. To Verify whether the "Book an Appointment" button is working and displaying the Interior Design Services page correctly. | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/products/paints-and-textures.html) 3. Look for interior design services section. 4. Click on Book an appointment button. | https://www.asianpaints.com/products/paints-and-textures.html | User should be able to see the Interior Design Services Section and land on booking page upon clicking. | User is able to see the Interior Design Services Section and land on booking page upon clicking. | Passed
TC_P&T_Calculator_Tools_01 | TS_P&T_Calculator_Tools | 1. User is able to successfuly land on Paints and Textures Page. | 1. Verify whether the Paint Budget Calculator, Colour Visualiser and Paint selector functionalities are displayed properly. 2. Verify whether all three are clickable and landing on correct page | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/products/paints-and-textures.html) 3. Locate calculator tools in the body section. 4. Click on all tools one by one and check if they land on correct page. | https://www.asianpaints.com/products/paints-and-textures.html | User should be able to see the Calculator Tools and land on correct pages upon clicking. | User is able to see the Calculator Tools and land on correct pages upon clicking. | Passed
TC_P&T_Paint_Budget_Calculator_01 | TS_P&T_Paint_Budget_Calculator | 1. User is able to successfully land on Paint Budget Calculator Page. OR 2. Test case "TC_P&T_Calculator_Tools_01" is passed. 3.User Should have the correct form data and expected result. | 1. To verify whether the user is able to use the paint budget calculator with correct data. | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/resources/tools/paint-budget-calculator.html) 3. Check if two Calculators (Quick Calculator and Advanced Calculator) are present on the page. PART A : 1. Select the Quick calculator. 2. Fill the form details by and select the Calculate Now button. PART B: 1. Select the Advanced Calculator. 2. Fill the form and select the Calculate Now button. 4. Repeat step 3 for all the different cobinations in form data(3 radio buttons). | https://www.asianpaints.com/resources/tools/paint-budget-calculator.html | User should be able to see the expected result. | User is a able to get the expected result. | Passed
TC_P&T_Paint_Budget_Calculator_02 | TS_P&T_Paint_Budget_Calculator | 1. User is able to successfully land on Paint Budget Calculator Page. OR 2. Test case "TC_P&T_Calculator_Tools_01" is passed. | 1. To verify whether the Quick Calculator is not accepting incorrect data into the Carpet Area field. | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/resources/tools/paint-budget-calculator.html) 3.Select Quick Calculator. 4. Enter following type of incorrect type of data into the Carpet area field: a) negative number b)alphanumeric c)blank field 5. Repeat step 4 for different combination of other form data(3 radio buttons). | https://www.asianpaints.com/resources/tools/paint-budget-calculator.html | 1. User should not be able to submit the form. 2.User should see proper warning for wrong entries. | 1. User is not able to submit the form. 2.User is getting proper warning for wrong entries. | Passed
TC_P&T_Paint_Budget_Calculator_03 | TS_P&T_Paint_Budget_Calculator | 1. User is able to successfully land on Paint Budget Calculator Page. OR 2. Test case "TC_P&T_Calculator_Tools_01" is passed. 3.User Should have the correct form data and expected result. | 1. To verify whether the Advance Calculator is not accepting incorrect data into the various fields. | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/resources/tools/paint-budget-calculator.html) 3.Select Quick Calculator. 4. Enter following type of incorrect type of data into the Width/Height/Length/Window/Door field one at a time: a) negative number b)alphanumeric c)blank field 5. Repeat step 4 for different combination of other valid form data | https://www.asianpaints.com/resources/tools/paint-budget-calculator.html | 1. User should not be able to submit the form. 2.User should see proper warning for wrong entries. | 1. User is not able to submit the form. 2.User is getting proper warning for wrong entries. | Passed
TC_P&T_Colour_Selector_01 | TS_P&T_Colour_Selector | 1. User is able to successfully land on Paint Selector Page. OR 2. Test case "TC_P&T_Calculator_Tools_01" is passed. | 1. Verify whether the Paint Selector page is working | 1. Open Browser 2.Enter URL (https://www.asianpaints.com/resources/tools/paint-selector.html). 3. Check whether the page is displayed with various products or not. 4. Check whether the product details and "View Product" button is present on mouse hover. 5. click on View Product button and check whether it leads to the correct product details page. 6. Repeat above steps for different products. | https://www.asianpaints.com/resources/tools/paint-selector.html | 1. User should be able to see the products on the page. 2. The View Product button and product details should be visible on mouse hover. 3. User should be able to see the correct product Detail page upon clicking View Product. | 1. User is able to see the products on the page. 2. The View Product button and product details is visible on mouse hover. 3. User is able to see the correct product Detail page upon clicking View Product. | Passed
TC_P&T_Colour_Selector_02 | TS_P&T_Colour_Selector | 1. User is able to successfully land on Paint Selector Page. OR 2. Test case "TC_P&T_Calculator_Tools_01" is passed. 3. Test case "TC_P&T_Colour_Selector_01" is passed. | 1. Verify whether "Filter By Functionality is working. | 1. Open Browser 2.Enter URL (https://www.asianpaints.com/resources/tools/paint-selector.html). 3. Click on "Filter By" dropdown. 4.Select differnt filter combinations. 5. Click "Clear All" button to see if the filters are unselected. 6. Repeat step 4 and click on "Apply" button. 7. Repeat step 6 for different combinations. | https://www.asianpaints.com/resources/tools/paint-selector.html | 1. User should be able to use "Filter By", "Clear All", and "Apply" button. with expected output. 2. User should see the correct filtered products. | 1. User is able to use "Filter By", "Clear All", and "Apply" button. with expected output. 2. User is able to see the correct filtered products. | Passed
TC_P&T_Colour_Selector_03 | TS_P&T_Colour_Selector | 1. User is able to successfully land on Paint Selector Page. OR 2. Test case "TC_P&T_Calculator_Tools_01" is passed. 3. Test case "TC_P&T_Colour_Selector_01" is passed. 4. User should have the correct login credentials. | 1. verify whether the "WishList" button is working | 1. Open Browser 2.Enter URL (https://www.asianpaints.com/resources/tools/paint-selector.html). 3. Click WishList icon on top right corner of each product. | https://www.asianpaints.com/resources/tools/paint-selector.html | 1.Logged In User should be able to add products to the wishlist. 2.For User that are not logged in , Login popup should appear | 1.Logged In User are able to add products to the wishlist. 2.For User that are not logged in , Login popup appear. | Passed
TC_P&T_UNIQUE_PAint Related Ideas/Services/Products | TS P&T_UNIQUE_PAint Related Ideas/Services/Products | 1. User is able to successfuly land on Paints and Textures Page. | 1. To verify whether "UNIQUE_PAint Related Ideas/Services/Products" section is present. 2. To verify all links are working in this section and leading to correct pages. | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/products/paints-and-textures.html). 3. Click on all available Links in this section. | https://www.asianpaints.com/products/paints-and-textures.html | User should be able to see this Section and land on correct pages upon clicking. | User is able to see this Section and land on correct pages upon clicking. | Passed
TC_ P&T_Explore_our_Stores | TS P&T_Explore_our_Stores | 1. User is able to successfuly land on Paints and Textures Page. | 1. To verify whether "Explore Our Stores" section is present. 2. To verify all links are working in this section and leading to correct pages. | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/products/paints-and-textures.html). 3. Click on all available Links. | https://www.asianpaints.com/products/paints-and-textures.html | User should be able to see this Section and land on correct pages upon clicking. | User is able to see this Section and land on correct pages upon clicking. | Passed
TC_P&T_Wall_Decals | TS_P&T_Wall_Decals | 1. User is able to successfuly land on Paints and Textures Page. | 1. To verify whether "Wall_Decals" section is present. 2. To verify all links are working in this section and leading to correct pages. | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/products/paints-and-textures.html). 3. Click on all available Links. | https://www.asianpaints.com/products/paints-and-textures.html | User should be able to see this Section and land on correct pages upon clicking. | User is able to see this Section and land on correct pages upon clicking. | Passed
TC_Safe_Painting_services | TS_Safe_Painting_services | 1. User is able to successfuly land on Paints and Textures Page. | 1. To verify whether "Safe_Painting_Services" section is present. 2. To verify all links are working in this section and leading to correct pages. | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/products/paints-and-textures.html). 3. Click on all available Links. | https://www.asianpaints.com/products/paints-and-textures.html | User should be able to see this Section and land on correct pages upon clicking. | User is able to see this Section and land on correct pages upon clicking. | Passed

## Test Scenarios - Sakshi
Priority | TestScenarioID | Requirement ID | Test Scenario Description | Type of Testing | Possible No. of TestCases | Test Case Details
P1 | TS_Navigation_01 (Header) | REQ_Navigation_01 | Verification of the Navigation section | Usability testing and Functional Testing | 10 | 1. To validate if the buttons in the navigation section are working and lead to relevant pages. 2. To validate that the navigation section should have a working "Design and Colour App" tab. 3. To validate that the navigation section should have a working "Find a Contractor" tab. 4. To validate that the navigation section should have a working "Find a Store" tab. 5. To validate that the navigation section should have a toll free number. 6. To validate that the navigation section should have a working "Home owners" drop down menu. 7. To validate that the navigation section should have a working "Wishlist" option. 8. To validate that the navigation section should have a working "Profile" option. 9. To validate that the navigation section should have a working "View Cart" option. 10. To validate if the "Search" bar is working.
| TS_Login_01 (Header) | REQ_Login_01 | Verification of the Login functionality | Functional testing | 7 | 1. To validate if the user is able to login using valid credentials (valid mobile number and OTP). 2. To validate if the user is able to login using invalid credentials (invalid mobile number and invalid OTP). 3. To validate if the user is able to login using invalid mobile number and valid OTP. 4. To validate if the user is able to login using valid mobile number and invalid OTP. 5. To validate if the user is able to login without any credentials. 6. To validate that after the user has logged in and browsing back using browser back button. 7. To validate the timeout of the login session. 8. To validate if "terms and conditions" page is opening before user types OTP
P2 | TS_Tools_01 (Footer) | REQ_Tools_01 | Verification of Tools Functionality | Usability testing and Functional testing | 2 | 1. To validate if the user is able to click on all the options 2. To validate if the user is navigated to specific pages after clicking on each button
| TS_StoreLocator_01 (Body) | REQ_StoreLocator_01 | Verification of Store Locator functionality | Usability testing and Functional testing | 7 | 1. To validate that "AP Beautiful Homes", "Colour Ideas", "Signature Stores" buttons work and navigates user to pages with more information about it 2. To validate that the user can enter pincode and click go button 3. To validate if user is able to go ahead without entering any pincode 4. To validate if user is redirected to another page after typing a pincode 5. To validate if user is able to find any stores with invalid pincode 6. To validate if user is able to check the location on Google maps 7. To validate if user is able to enter mobile number and email for getting information about the dealer
| TS_Enquiry_01 (Body) | REQ_Enquiry_01 | Verification of Enquiry functionality | Functional testing | 3 | 1. To Validate if the user is able to enter valid credentials 2. To validate if the user is able to enter invalid credentials and enquire 3. To validate if the user is able to enquire without providing any credentials
P3 | TS_Shop_01 (Body) | REQ_Shop_01 | Verification of Shop Functionality | Usability testing | 2 | 1. To validate if the user is able to view suggested products on the homepage 2. To validate if the user is navigated to shop page after clicking on "View all"
P4 | TS_MobileApp_01 (Body) | REQ_MobileApp_01 | Verification of Mobile app functionality | Usability testing and functional testing | 3 | 1. To validate if user is able to download app on Appstore and Playstore 2. To validate if the user is able to enter mobile number to get link to the app through SMS 3. To validate if "get link" button is working
| TS_About&Policies_01 (Footer) | REQ_About&Policies_01 | Verification of About and Policies functionality | Usability testing and functional testing | 3 | 1. To validate if user is able to click on all the options available and gets redirected to other page 2. To validate if user is able to enter details under warranty claim 3. To validate if user are able to enter invalid details under warranty claim
| TS_InteriorDesign_01 (Body) | REQ_InteriorDesign_01 (Body) | Verification of Interior design functionality | Usability testing and Functional testing | 5 | 1. To validate if user is able to view few examples of Interior design services 2. To validate if user is able to click on "book an appointment" 3. To validate if user is able to book an appointent with valid credentials 4. To validate if user is able to book an appointment with invalid credentials 5. To validate if user is able to book an appointment without providing any credentials
Note on H2: Lemme know if Navigation section is fine? -Sakshi Jamanani

## Home Page
Issue Type | Summary | Priority
Epic 1 | Header
Story 1 | As a user, I want a navigation section, so that user can navigate to different sections. | P1
Story 2 | As a user, I want to have Login feature so that i can access Login functionality | P1
Story 3 | As a user, I want a dropdown so that, user can select their user/product profile | P3
Story 4 | As a user I want to see all the available services and products in dropdown so that I can make my decision. | P1
Story 5 | As a user, I want a search bar so that user can search for their requirement. | P3
Epic 2 | Body
Story 1 | As a user, I want a Store Locater so that user can find stores based on pincode | P2
Story 2 | As a user I want to have an Interior Design Section so that I can access the Asian Paints Interior design Service and book an appointment | P4
Story 3 | As a user I should be able to download the app from PlayStore or the AppStore so that I can understand what different styles suit my home | P4
Story 4 | As a user, I want a section for viewing all the categories of Asian Paints products available | P3
Story 5 | As a used, I want a section where I can provide details and request for an enquiry | P2
Epic 3 | Footer
Story 1 | As a user, I want to know about company and its policies, so that I can get to know the company | P4
Story 2 | As a user, I want to navigate to the tools provided by the company, so that I can use them. | P2

## Test Scenarios - Yogesh
Priorities | TestScenarioID | Requirement ID | Test Scenario Description | Type of Testing | Possible No. of TestCases | Test Case Details
P2 | TS_P&T_TAB_01 | REQ_Paint&Textures_01 | Verifyth working of Paints and Textures Tab | Usability Testing | 3 | 1. To verify whether the user is able to click on the Paints and Textures Tab. 2. To Verify if the contents of Paints and Textures Tab are visible on the page. 3. To check whether the contents on the tab are visible on mouse hover.
P5 | TS_P&T_Body_01 | REQ_Paint&Textures_01 | Verify the tiles update | Usability Testing | 1 | 1. Verify whether the desired tiles are updating.
P2 | TS_P&T_PaintSelection_01 | REQ_Paint_Selection_01 | Verify all the colors and textures available/selectable for exterior,interiors and water proofing ,wood & metal | Functional Testing | 3 | 1. To verify whether This section is present or not. 2. To Verify if all the four tiles in this section are clickable or not. 3. To verify whether the user lands on correct pages after clicking the links.
P4 | TS_P&T_Wall/Paint_Ideas | REQ_Explore_Ideas | Verify Whether the Explore Ideas page is woking | Functional Testing | 4 | 1. To verify Whether the section is present. 2. To verify it lands on correct Page. 3. To verify the page has different Ideas. 4. To verify whether the landed page appropriate filter for ideas and are working.
P2 | TS_P&T_Interior_Design_Services | REQ_Interior_Design_Services_01 | Verify whether the user is able to access Interior Design Services and book for the same | Functional Testing | 2 | 1. To verify whether the Interior design Section is correctly displayed or not. 2. To Verify whether the "Book an Appointment" button is working and displaying the Interior Design Services page correctly.
P2 | TS_P&T_Calculator_Tools | REQ_Paint_Budjet_ColorVisualiser_PaintSelector | Verify whether the Paint Budjet Calculator, Colour Visualiser and Paint selector functionalities are working | Usability Testing | 1 | 1. To verify whether these three functinalities are displaying correctly and clickable and landing on correct page.
P2 | TS_P&T_Paint_Budjet_Calculator | REQ_Paint_Budjet_Calculator | Verify whether the paint Budjet Calculator page is working | Functional Testing | 3 | 1. To verify whether the forms(Simple Calculator or Advance) are displaying. 2. To verify whether the form are fillable and accepting correct entries. 3. To verify the forms can be submitted and show the correct results.
P2 | TS_P&T_Colour_Selector | REQ_Colour_Selctor | Verify whether the Paint Selector page is working | Functional Testing | 1 | 1. To verify whether the page is displaying various products and any product can be selected to see the details. 2. To verify the Filters are working. 3. To verify the wishlist icon is working correctly and only for logged in users
| TS P&T_UNIQUE_PAint Related Ideas/Services/Products | REQ_UNIQUE_PAint Related Ideas/Services/Products | Verify whether this section is working | Usability testing | 3 | 1. To verify Whether the section is present. 2. To verify it lands on correct Page. 3. To verify the Section has different Produts/IdeasServices.
P3 | TS P&T_Explore_our_Stores | TS P&T_Explore_our_Stores | Verify whether this section is working | Usability testing | 2 | 1. To verify Whether the section is present. 2. To verify it lands on correct Page.
P5 | TS_P&T_Wall_Decals | REQ_P&T_Wall_Decals | Verify whether this section is working | Usability testing | 2 | 1. To verify Whether the section is present. 2. To verify it lands on correct Page.
P6 | TS_Safe_Painting_services | REQ_Safe_Painting_services | Verify whether the Safe Painting Services are available and user can use them | Usability testing | 2 | 1. To verify Whether the section is present. 2. To verify it lands on correct Page.

## Paints & Textures
Issue Type | Summary | Priority
Epic 1 | Body
Story 1 | As a user, I want tiles update for Paints and textures tab so that I can see what is available in the page | P5 | done
Story 2 | As a user, I want a section for selecting paint types based on my needs. | P2
Story 3 | As a user, I want a section to explore wall/Paint ideas for different spaces so that I don't have to browse internet seperately | P4 | In ideas page
Story 4 | As a user, I want a section for exploring and accessing interior design services so that I can book an appointment if needed | P2
Story 5 | As a user, I want to use different tools like budget, color visualizer, paint selector by providing the details and getting personalized choices | P2
Story 6 | As a user, I want to know about Unique paint related services/Ideas/Products so that I can use them. | P3 | already covered under different sections
Story 7 | As a user, I want a "Explore our stores" section so that I can find stores based on pincode. | P3 | already covered
Story 8 | As a user, I want a "Wall Decals" section so that I can buy wall stickers. | P5 | already covered under shop
Story 9 | As a user I want an enquiry section for Asian Paint Safe Painting Service so that I can clear my doubts and book for the service | P6
Story 10 | Services (As a user, I want to fill the enquiry form so that I can avail a free site evaluation visit) | P6 | alredy covered

## Test Scenarios - Ananth
Priority | TestScenarioID | Requirement ID | Test Scenario Description | Type of Testing | Possible No. of TestCases | Test Case Details
1 | TS_Idea Functionality_01 | REQ_Idea Functionality_01 | Verification of whether the user can view all the styles/tiles available | Usability Testing | 2 | 1. To validate that the user is able to search for desired styles by clicking on the tiles shown 2. To validate that the user can play the videos shown under "Where the heart is" drop down
| TS_Signout Functionality_01 | REQ_Signout Functionality_01 | Verification of whether the user can Sign out successfully | Functional Testing | 6 | 1. To validate that the user is able to sign out of their profile by clicking the "Sign out" option under the "Profile" icon found in the header 2. To validate the application session status, after logging in and closing the Browser without logging out 3. To validate logging out and clicking the back button 4. To validate the "Sign out" option is not visible before logging into the user's profile 5. To validate the "Sign out" and "Sign in" immediately after logging out 6. To validate "Sign out" functionality in all supported environments
2 | TS_Idea Functionality_02 | REQ_Idea Functionality_02 | Verification if user upon filling the "Enquiry Form" receives communication regarding the free site evaluation | Functional Testing | 7 | 1. To validate whether the user is able to fill in his details into the "Enquiry form" 2. To validate if the functionality works if user enters invalid email Id and valid username 3. To validate if the functionality works if the user enters valid email ID and invalid phone number 4. To validate if the functionality works if the user enters valid Email Id, valid Username, valid phone number and invalid pincode 5. To validate if the "Enquire now" button is functioning 6. To validate if the "Download the Asian Paints Color Book" button is working 7. To validate if the "Enquire now" button functions without entering any of the fields required
| TS_ViewOrder_User's profile_02 | REQ_ViewOrder_User's profile_02 | To validate if the "View details" button when clicked, leads to current/past orders | Functional Testing | 3 | 1. To validate if the user can click on the "My order" tab 2. To validate if the "View details" button when clicked, leads to current/past orders 3. To validate if the "Close" button when clicked leads back to the list of past/current orders
3 | TS_Idea Functionality_03 | REQ_Idea Functionality_03 | Verification if the filter option works for users under the "Ideas Gallery" and "Blogs" section | Functional Testing | 6 | 1. To validate if the functionality works if we select an option from only "Color" in the "Ideas Gallery" option 2. To validate if the functionality works if we select an option from "Color" and "Product Type" in the "Ideas Gallery" option 3. To validate if the functionality works if we select all the options in the "Ideas Gallery" option 4. To validate if the functionality works if we select an option from "Waterproofing issues" in the "Blogs" option 5. To validate if the functionality works if we select an option from "Waterproofing issues" and "Areas" in the "Blogs" option 6. To validate if the functionality works if we select all options from in the "Blogs" option
| TS_ViewOrder_User's profile_03 | REQ_ViewOrder_User's profile_03 | To validate if the user is able to edit their profile in the "My Profile" tab using "Edit" button | Functional Testing | 1 | 1. To validate if the user is able to edit their personal details in the "My Profile" tab
4 | TS_ViewOrder_User's profile_04 | REQ_ViewOrder_User's profile_04 | To validate if user can upload bills for reference onto the "My Documents" tab using "Add New Bill" button | Functional Testing | 2 | 1. To validate if the user is able to upload bills using the "Add New Bill" button on the "My Documents" tab 2. To validate if user can delete existing documents under the "My Documents" tab
27

## Test Cases - Ananth
Test Case ID | Test Scenario | Precondition | Test Condition | Test Case Steps | Test Data | Expected Result | Actual Result Iteration 1 | Status Iteration 1 | Actual Result Iteration 2 (to be updated only if test case failed in Iteration 1) | Status Iteration 2 (to be updated only if test case failed in Iteration 1) | Comments | Req: Reference
<Sequence number> | <Identify test scenarios> | <This cell specifies the state a system and its environment must be in before this specific test case can be run> | <This cell describes what to test for i.e. the condition which is being tested for> | <This cell describes how to test i.e. the detailed testing procedure> | <Mention test data to be used> | <Describe the expected test result> | <Describe the actual test result after execution of test cases. In case screenshots need to be attached to substantiate the test result, use the references tab.> | Status of the test case whether it got passed/ failed/Hold in interation 1. | <Describe the actual test result after execution of test cases second time. In case screenshots need to be attached to substantiate the test result, use the references tab.> | New status of test case after it failed in Iteration 1.
TC_Idea Functionality_01 | TS_Idea Functionality_01 | 1. User is able to search for the required styles | To validate that the user is able to search for desired styles by clicking on the tiles shown | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) for the website 3. Hover on the "Ideas" option in the header 4. Select any option below that to view styles/ideas | https://www.asianpaints.com/ | Upon clicking any style shown in the website, more information should be visible | Upon clicking on the tiles/text fields in certain places, more information about that style is visible | Passed
TC_Idea Functionality_02 | TS_Idea Functionality_01 | 1. User is able to click on the videos and view them in the "Where the heart is" dropdown 2. User is able to play the video once the tile is clicked by clicking on the "Play" Button | To validate that the user can play the videos shown under "Where the heart is drop down" | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) for the website 3. Hover on the "Ideas" option in the header 4. Select the "Where the heart is" option in the drop down 5. Click on any of the videos | https://www.asianpaints.com/where-the-heart-is/season-5.html | Upon clicking the videos shown under the "Where the heart is" dropdown, it should lead to another page where the videos start playing when you click on the "Play" symbol | Upon clicking the "Play" symbol, the videos start playing | Passed
TC_Signout Functionality_01 | TS_Signout Functionality_01 | 1. User is able to sign out successfully 2. User must have valid credentials 3. User is signed out upon clicking the "Sign out" button | To validate that the user is able to sign out of their profile by clicking the "Sign out" option under the "Profile" icon found in the header | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) for the website 3. Navigate to the "Profile" icon on the header and click it 4. Sign in using valid credentials 5. Click on "Sign out" option in the profile drop down | https://www.asianpaints.com/ | Upon clicking the "Sign out" option, the user must be successfully signed out from their account | User is signed out of their account successfully | Passed
TC_Signout Functionality_02 | TS_Signout Functionality_01 | 1. User is signed out when the user closes the browser without clicking on the "Sign out" option 2. User must have valid credentials | To validate the application session status, after logging in and closing the Browser without logging out | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) for the website 3. Navigate to the "Profile" icon on the header and click it 4. Sign in using valid credentials 5. Close the browser 6. Open the URL again | https://www.asianpaints.com/ | Upon closing the browser and opening the URL again, the user must be asked to "Sign in" again | User is still logged in when the URL is opened | Failed
TC_Signout Functionality_03 | TS_Signout Functionality_01 | 1. User must be signed out when they click on the back button 2. User must have valid credentials | To validate logging out and clicking the back button | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) for the website 3. Navigate to the "Profile" icon on the header and click it 4. Sign in using valid credentials 5. Click on the "Back" button on the browser 6. Open the URL again | https://www.asianpaints.com/ | Upon clicking the back button, the user must be logged out of their account and must be asked to log in again when they open the URL | User is still logged in when the URL is opened | Failed
TC_Signout Functionality_04 | TS_Signout Functionality_01 | 1. User must not be able to view the "Sign out" option on the "Profile" icon when the user has not yet logged in 2. User must have valid credentials | To validate the "Sign out" option is not visible before logging into the user's profile | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) for the website 3. Navigate to the "Profile" icon on the header and click it | https://www.asianpaints.com/ | The "Sign out" option should not be visible when the user clicks on the "Profile" option | The "Sign out" option is not visible to the user without signing into their profile | Passed
TC_Signout Functionality_05 | TS_Signout Functionality_01 | 1. User must be already logged into the website 2. User must log in with valid credentials using same account or different account | To validate the "Sign out" and "Sign in" immediately after logging out | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) for the website 3. Navigate to the "Profile" icon on the header and click it 4. Sign in using valid credentials 5. Click on "Sign out" option in the profile drop down 6. Click on "Sign in" option again using same or different account 7. Click on the "Sign out" option available in the Profile tab | https://www.asianpaints.com/ | User should be able to view the "Sign out" option once they have logged in again | The "Sign out" option is visible to the user once they have logged in again | Passed
TC_Signout Functionality_06 | TS_Signout Functionality_01 | 1. User must be able to log out through different browsers after logging in 2. User must have valid credentials | To validate "Sign out" functionality in all supported environments | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) for the website in different browsers 3. Navigate to the "Profile" icon on the header and click it 4. Sign in using valid credentials 5. Click on "Sign out" option in the profile drop down | https://www.asianpaints.com/ | Upon clicking the "Sign out" option, the user must be successfully signed out from their account | User is signed out of their account successfully | Passed
TC_Idea Functionality_01 | TS_Idea Functionality_02 | 1. User is able to enter data into the fields provided 2. User has the required data for the enquiry form | To validate whether the user is able to fill in his details into the enquiry form | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) for the website 3. Navigate to the "Ideas" section in the Navigation Section and hover over it 4. Click on the "Ideas Gallery" option 5. Fill in the necessary credentials and click on the "Enquire now" button | https://www.asianpaints.com/inspiration/ideas/inspiration-gallery.html | User should get a message informing that a representative will get back to them about the site visit and the user should be able to download the "Asian Paints Color Book" | User gets the message about the site visit and is also able to download the book | Passed
TC_Idea Functionality_02 | TS_Idea Functionality_02 | 1. User is able to enter data into the fields provided 2. User has the required data for the enquiry form | To validate if the functionality works if user enters invalid email Id and valid username | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) for the website 3. Navigate to the "Ideas" section in the Navigation Section and hover over it 4. Click on the "Ideas Gallery" option 5. Enter invalid email ID and valid username along with other credentials as requested | https://www.asianpaints.com/inspiration/ideas/inspiration-gallery.html | User should not be able to proceed with the "Enquire now button" instead, an error message should be prompted | User is faced with an error which states "Email is invalid" | Passed
TC_Idea Functionality_03 | TS_Idea Functionality_02 | 1. User is able to enter data into the fields provided 2. User has the required data for the enquiry form | To validate if the functionality works if the user enters valid email ID and invalid phone number | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) for the website 3. Navigate to the "Ideas" section in the Navigation Section and hover over it 4. Click on the "Ideas Gallery" option 5. Enter valid email ID and invalid phone number along with other credentials as requested | https://www.asianpaints.com/inspiration/ideas/inspiration-gallery.html | User should not be able to proceed with the "Enquire now button" instead, an error message should be prompted | User is faced with an error which states "Phone number is invalid" | Passed
TC_Idea Functionality_04 | TS_Idea Functionality_02 | 1. User is able to enter data into the fields provided 2. User has the required data for the enquiry form | To validate if the functionality works if the user enters valid Email Id, valid Username, valid phone number and invalid pincode | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) for the website 3. Navigate to the "Ideas" section in the Navigation Section and hover over it 4. Click on the "Ideas Gallery" option 5. Enter valid email ID, valid username and valid phone and invalid pincode | https://www.asianpaints.com/inspiration/ideas/inspiration-gallery.html | User should not be able to proceed with the "Enquire now button" instead, an error message should be prompted | User is faced with an error which states "Phone number is invalid" | Passed
TC_Idea Functionality_05 | TS_Idea Functionality_02 | 1. User is able to enter data into the fields provided 2. User has the required data for the enquiry form | To validate if the "Enquire now" button is functioning | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) for the website 3. Navigate to the "Ideas" section in the Navigation Section and hover over it 4. Click on the "Ideas Gallery" option 5. Enter valid email ID, valid username and valid phone number and valid pincode | https://www.asianpaints.com/inspiration/ideas/inspiration-gallery.html | User should be able to click on the enquire now button and is led to the next page with a confirmation message and an option to download the brochure | User is led to a page with confirmation message and is also allowed to download the brochure | Passed
TC_Idea Functionality_06 | TS_Idea Functionality_02 | 1. User is able to enter data into the fields provided 2. User has the required data for the enquiry form | To validate if the "Download the Asian Paints Color Book" button is working | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) for the website 3. Navigate to the "Ideas" section in the Navigation Section and hover over it 4. Click on the "Ideas Gallery" option 5. Enter valid credentials 6. Click on the "Download the Asian Paints Color Book" button | https://www.asianpaints.com/inspiration/ideas/inspiration-gallery.html | User should be able to view a PDF with the required information | User is able to view the PDF with information | Passed
TC_Idea Functionality_07 | TS_Idea Functionality_02 | 1. User is able to enter data into the fields provided 2. User has the required data for the enquiry form | To validate if the "Enquire now" button functions without entering any of the fields required | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) for the website 3. Navigate to the "Ideas" section in the Navigation Section and hover over it 4. Click on the "Ideas Gallery" option 5. Do not enter anything into the credentials field 6. Click on the "Enquire Now" button | https://www.asianpaints.com/inspiration/ideas/inspiration-gallery.html | User should not be able to proceed with the "Enquire now button" instead, an error message should be prompted | User is prompted with a "Field is required" comment under each of the required credentials | Passed
TC_ViewOrder_User's profile_01 | TS_ViewOrder_User's profile_02 | 1. User has placed an order in the past 2. User must have signed into the application | To validate if the user can click on the "My order" tab | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) for the website 3. Navigate to the "Profile" icon on the header and click it 4. Sign in using valid credentials 5. Click on the "My Profile" icon in the Profile button. 6. Click on the "My Orders" tab | https://www.asianpaints.com/ | User is presented with a list of all past/current orders made by them | List of orders is showcased along with status | Passed
TC_ViewOrder_User's profile_02 | TS_ViewOrder_User's profile_02 | 1. User has placed an order in the past 2. User must have signed into the application | To validate if the "View details" button when clicked, leads to current/past orders | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) for the website 3. Navigate to the "Profile" icon on the header and click it 4. Sign in using valid credentials 5. Click on the "My Profile" icon in the Profile button. 6. Click on the "My Orders" tab 7. Click on "View Details" button on the most recent order made | https://www.asianpaints.com/ | User is presented with more information about his current order | Button leads to more information being displayed on the screen for the user | Passed
TC_ViewOrder_User's profile_03 | TS_ViewOrder_User's profile_02 | 1. User has placed an order in the past 2. User must have signed into the application | To validate if the "Close" button when clicked leads back to the list of past/current orders | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) for the website 3. Navigate to the "Profile" icon on the header and click it 4. Sign in using valid credentials 5. Click on the "My Profile" icon in the Profile button. 6. Click on the "My Orders" tab 7. Click on "View Details" button on the most recent order made 8. Click on the "Close" button | https://www.asianpaints.com/ | User is presented with a list of all orders made by them | List of current and past orders is presented to the user | Passed
TC_Idea Functionality_01 | TS_Idea Functionality_03 | 1. User should be able to view all the filter options in both the "Ideas Gallery" section and the "Blogs" section | To validate if the functionality works if we select an option from only "Color" in the "Ideas Gallery" option | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) for the website 3. Navigate to the "Ideas" section in the Navigation Section and hover over it 4. Click on the "Ideas Gallery" option 5. Navigate to the filter option on the left side as you scroll down 6. Select an option only from "Color" | https://www.asianpaints.com/inspiration/ideas/inspiration-gallery.html | User is presented with the tiles specific to their choices | User is able to view according to the options they have selected | Passed
TC_Idea Functionality_02 | TS_Idea Functionality_03 | 1. User should be able to view all the filter options in both the "Ideas Gallery" section and the "Blogs" section | To validate if the functionality works if we select an option from "Color" and "Product Type" in the "Ideas Gallery" option | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) for the website 3. Navigate to the "Ideas" section in the Navigation Section and hover over it 4. Click on the "Ideas Gallery" option 5. Navigate to the filter option on the left side as you scroll down 6. Select an option from both "Color" and "Product Type" | https://www.asianpaints.com/inspiration/ideas/inspiration-gallery.html | User is presented with the tiles specific to their choices | User is able to view according to the options they have selected | Passed
TC_Idea Functionality_03 | TS_Idea Functionality_03 | 1. User should be able to view all the filter options in both the "Ideas Gallery" section and the "Blogs" section | To validate if the functionality works if we select all the options in the "Ideas Gallery" option | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) for the website 3. Navigate to the "Ideas" section in the Navigation Section and hover over it 4. Click on the "Ideas Gallery" option 5. Navigate to the filter option on the left side as you scroll down 6. Select an option from all the fields provided | https://www.asianpaints.com/inspiration/ideas/inspiration-gallery.html | User is presented with the tiles specific to their choices | User is able to view according to the options they have selected | Passed
TC_Idea Functionality_04 | TS_Idea Functionality_03 | 1. User should be able to view all the filter options in both the "Ideas Gallery" section and the "Blogs" section | To validate if the functionality works if we select an option from "Waterproofing issues" in the "Blogs" option | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) for the website 3. Navigate to the "Ideas" section in the Navigation Section and hover over it 4. Click on the "Blogs" option 5. Navigate to the filter option on the left side as you scroll down 6. Select an option from "Waterproofing issues" | https://www.asianpaints.com/blogs.html | User is presented with the tiles specific to their choices | User is able to view according to the options they have selected | Passed
TC_Idea Functionality_05 | TS_Idea Functionality_03 | 1. User should be able to view all the filter options in both the "Ideas Gallery" section and the "Blogs" section | To validate if the functionality works if we select an option from "Waterproofing issues" and "Areas" in the "Blogs" option | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) for the website 3. Navigate to the "Ideas" section in the Navigation Section and hover over it 4. Click on the "Blogs" option 5. Navigate to the filter option on the left side as you scroll down 6. Select an option from "Waterproofing issues" and "Areas" | https://www.asianpaints.com/blogs.html | User is presented with the tiles specific to their choices | User is able to view according to the options they have selected | Passed
TC_Idea Functionality_06 | TS_Idea Functionality_03 | 1. User should be able to view all the filter options in both the "Ideas Gallery" section and the "Blogs" section | To validate if the functionality works if we select all options from in the "Blogs" option | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) for the website 3. Navigate to the "Ideas" section in the Navigation Section and hover over it 4. Click on the "Blogs" option 5. Navigate to the filter option on the left side as you scroll down 6. select an option from all fields | https://www.asianpaints.com/blogs.html | User is presented with the tiles specific to their choices | User is able to view according to the options they have selected | Passed
TC_ViewOrder_User's profile_01 | TS_ViewOrder_User's profile_03 | 1. User should have logged into their profile 2. User must have valid credentials | To validate if the user is able to edit their profile in the "My Profile" tab using "Edit" button | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) for the website 3. Navigate to the "Profile" icon on the header and click it 4. Sign in using valid credentials 5. Click on the "My Profile" icon in the Profile button. 6. Go to the "My Profile" tab and click on "Edit" | https://www.asianpaints.com/ | User is allowed to edit their details | User can successfully change their details if required as the button allows them to do so | Passed
TC_ViewOrder_User's profile_01 | TS_ViewOrder_User's profile_04 | 1. User should have logged into their profile 2. User must have valid credentials | To validate if user can upload bills for reference onto the "My Documents" tab using "Add New Bill" button | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) for the website 3. Navigate to the "Profile" icon on the header and click it 4. Sign in using valid credentials 5. Click on the "My Profile" icon in the Profile button. 6. Go to the "My Documents" tab and click on "Add New Bill" | https://www.asianpaints.com/ | User is able to upload documents onto the application | User can successfully upload bills onto the application | Passed
TC_ViewOrder_User's profile_02 | TS_ViewOrder_User's profile_04 | 1. User should have logged into their profile 2. User must have valid credentials 3. User must have documents uploaded already | To validate if user can delete existing documents under the "My Documents" tab | 1. Open Browser 2. Enter URL (https://www.asianpaints.com/) for the website 3. Navigate to the "Profile" icon on the header and click it 4. Sign in using valid credentials 5. Click on the "My Profile" icon in the Profile button. 6. Go to the "My Documents" tab and click on "Delete" | https://www.asianpaints.com/ | User is able to delete documents of their choice | User can successfully delete bills from the application | Passed

## Shop
Issue Type | Summary | Priority
Epic 1 | Shopping for items
Story 1 | As a user, I should be able to search for different wallpaper and wallstickers so that I can get a variety of results | P2
Story 2 | As a user, I should be able to purchase a color selection tool so that I can make an informed choice among the colors | P1
Story 3 | As a user, I want to view the different options available for me to shop from so that I can choose from the variety shown in the slider images | P4
Story 4 | As a user I want to add to cart certain products so that I can buy them later | P1
Story 5 | As a user, I want to buy an item instantly when I click on the 'Buy Now' option | P1
Story 6 | As a user, I would like to select 'Cash on Delivery' option to make a payment | P1 | In case Amount is <=5000, COD works
Story 7 | As a user, I would like to make an online payment for the products that I have added to my cart so that it is convenient | P1 | In case Amount>5000, Pay now option will be enabled

## Test Scenarios - Divyansh
Priorities | TestScenarioID | Requirement ID | Test Scenario Description | Type of Testing | Possible No. of TestCases | Test Case Details
1 | TS_Shop_01 | REQ_Shop_01 | Verification of category "Color Selection Tools" under "Shop" | Usability Testing | 3 | 1.To validate that"Color Selection Tool" category is shown under "Shop". 2. To validate that the content under "Color Selection tool" is being displayed. 3 To validate if the tool description is being displayed.
| TS_Shop_02 | REQ_Shop_02 | Verification that user can purchase "Color selection tool" under "Shop" | Funtionality Testing | 4 | 1 To validate whether we can select "add to cart" and the pay for the color selection tool. 2 To validate if can use "buy now" for the color selection tool and pay for it. 3. To validate if user is able to select the quantity using the dropdown in the description page. 4. To validate if user can enter a number in "quantity" at the checkout page
| TS_Shop_03 | REQ_Shop_03 | Verification that user can add products to cart from any category under "Shop" section. | Funtionality Testing | 8 | 1. To validate if we can select products from "Wall stickers" can be added to cart. 2.To validate if we can select products from "Peel and stick" can be added to cart. 3.To validate if we can select products from "wallpapers" can be added to cart. 4.To validate if we can select products from "Do it yourself" can be added to cart. 5.To validate if we can select products from "Mechanized tools" can be added to cart. 6.To validate if we can select products from "Mask and PPE" can be added to cart. 7.To validate if we can select products from "Books and Catalogues" can be added to cart. 8.To validate if we can select products from "Adhesives" can be added to cart.
| TS_Shop_04 | REQ_Shop_04 | Verification that whether a product under "Shop" can be brought using "Buy Now" button. | Funtionality Testing | 2 | 1 To verify whether a user will be redirected to payment page using the "Buy now" without signing in . 2 To validate that user will be redirected to payment page using the "Buy now" option after signing in .
| TS_Shop_05 | REQ_Shop_05 | Verification of the COD option in payments page. | Funtionality Testing | 3 | 1.To verify that COD is available for a total product value below 5K. 2.To verify that COD is not available for a total product value above 5K. 3. To verify that displayed promocode is applicable for COD.
| TS-Shop_06 | REQ_Shop_06 | To check that user has option to make online payments | Funtionality Testing | 4 | 1. To check whether online payment is available when purchasing products under 5K using "Buy Now". 2.To check whether online payment is available when purchasing products above 5K using "Buy Now". 3.To verify online payment is available when purchasing products after adding them to cart using "Add to Cart". 4. To verify that most of the online payment methods are available in the payment page.
| TS_Shop_07 | REQ_Shop_07 | To verify the functioning of pincode feature | Functionality Testing | 2 | 1 To verify the functionality of pincode bar shown within categories. 2 To verify the functionality of pincode bar shown within item display.
2 | TS_Shop_08 | REQ_Shop_08 | To verify that all the items available in the category can be searched from the search bar | Functionality Testing | 1 | 1 To verify that user is able to search of items that are under "Shop" section
4 | TS_Chop_09 | REQ_Shop_09 | To verify functioning of slider images | Functionality Testing | 2 | 1 To verify that all the images are being displayed and are sliding.. 2 To verify that all the clickable and are redirecting user
Note on I4: Try it out and ping me if you need any help.. -Ananth Dharmavaram its resolved, thanks -Divyansh Singh

## Test Case-Divyansh
Test Case ID | Test Scenario | Precondition | Test Condition | Test Case Steps | Test Data | Expected Result | Actual Result Iteration 1 | Status Iteration 1
<Sequence number> | <Identify test scenarios> | <This cell specifies the state a system and its environment must be in before this specific test case and thenrun> | <This cell describes what to test for i.e. the condition which is being tested for> | <This cell describes how to test i.e. the detailed testing procedure> | <Mention test data to be used> | <Describe the expected test result> | <Describe the actual test result after execution of test cases. In case screenshots need to be attached to substantiate the test result, use the references tab.> | Status of the test case whether it got passed/ failed/Hold in interation 1.
TC_Shop_01 | TS_Shop_01 | 1.Open the application https://www.asianpaints.com/ in any browser. | To validate that "Color selection tool"category is shown under shop | 1. Open the url in browser and sign in 2. Click on "Shop" option below the search bar 3. Scroll down in the pages so that all categories are visible. | https://www.asianpaints.com/ | "Color Selection Tool"category will be displayed among other categories. | "Color Selection Tool"category was displayed among other categories. | PASS
TC_Shop_02 | TS_Shop_01 | 1.Open the application https://www.asianpaints.com/ in any browser. | To validate that content under "Color selection tool"category is shown. | 1.Open the url in browser and sign in. 2.Click on "Color Selection Tool" category after scrolling down. 3. Scroll down on the page to see the available items. | https://www.asianpaints.com/online-shop.html | 1.After clicking "Color selection tool" category, the website refreshes and the category opens in a new page. 2.All the items sold under "Color selection tool" are displayed .Their price and "Add to cart button" is visible. | 1.After clicking "Color selection tool" category, the website refreshes and the category opens in a new page. 2.All the items sold under "Color selection tool" are displayed .Their price and "Add to cart button" is visible. | PASS
TC_Shop_03 | TS_Shop_01 | 1.Open the application https://www.asianpaints.com/ in any browser. | To validate that items description of all the items is shown. | 1.Open the url in browser and sign in. 2.Click on the each item shown and scroll down to see the complete description. | https://www.asianpaints.com/online-shop/colour-selection-tools.html | 1.After clicking on image of the items displayed, a new page will open up. 2. That new page will have all the details of the product and an option to buy the selected product. 3. User will have an option to increase the quantity of the desired item, as long as that many pieces are in stock. | 1.After clicking on image of the items displayed, a new page opens up. 2. That new page has all the details of the product and an option to buy the selected product. 3. User can increase the quantity of the desired item, as long as that many pieces are present in the stock. | PASS
TC_Shop1_01 | TS_Shop_02 | 1.Open the application https://www.asianpaints.com/ in any browser. 2. Go to "Shop" using the redirect button below the search bar. 3.Open the 'Color Selection Tool" category. | To validate whether usercan add to cart the item under "Color selection tool" and then buy it using online and Cash on Delivery method | 1. Open the url in the browser and sign in. 2. Click on "Add to Cart" button only once.(ER-1) 3. Continue to click on 'Add to Cart' button repeatedly.(ER-2) | https://www.asianpaints.com/online-shop/colour-selection-tools.html | ER-1. After clicking it once, only one item is add to cart. ER-2. Repeated clicking causes the item to get add mulitple times. | 1. Only 1 item was add to the cart when add to cart is clicked once. 2. The quantity of the same item increases by one with every repeated click on the add to cart button. | PASS
TC_Shop1_02 | TS_Shop_02 | 1.Open the application https://www.asianpaints.com/ in any browser. 2. Go to "Shop" using the redirect button below the search bar. 3.Open the 'Color Selection Tool" category. | To validate whether usercan use 'Buy now' button for the products under "Color Selection Tool" catergory | 1.Open the url in browser and sign in 2.Click on any item shown. 3. Scroll down to and click on 'Buy Now' Button | https://www.asianpaints.com/online-shop/colour-selection-tools.html | 1. After clicking 'buy now', the page wil reload and deisplaya new checkout page. 2. The new page should have the total payable amount for all the items in user cart along with the item for which "Buy Now " was pressed. | 1. After clicking 'buy now', the page reloaded and displayed a new checkout page. 2. The new page had the total payable amount for all the items present in the cart along with the item for which "Buy Now " was pressed. | PASS
TC_Shop1_03 | TS_Shop_02 | 1.Open the application https://www.asianpaints.com/ in any browser. 2. Go to "Shop" using the redirect button below the search bar. 3.Open the 'Color Selection Tool" category. | To validate if user is able to select the quantity from the dropdown given in the product description. | 1 Open url in browser and sign in 2 Click on any item displayed. 3 Select the quantity option and select a value(min 1 , max varies for different item) and click on "Add to cart" 4.Check the "Shopping Bag' for the contents.(ER-1) 5 Select quantity and press "Add to cart" again for the same item. Check the "Shopping bag" for the content. (ER-2) | https://www.asianpaints.com/online-shop/colour-selection-tools.html | 1 (ER-1) The selected quantity will be shown in the shopping bag with the payable amount. 2 (ER-2) The new selected quantity should be add to the existing quantity in the "Shopping Bag" and the new payable amount is shown. | 1 (ER-1) The selected quantity is shown in the shopping bag with the payable amount. 2 (ER-2) The new selected quantity is add to the existing quantity in the "Shopping Bag" and the new payable amount is shown. | PASS
TC_Shop1_04 | TS_Shop_02 | 1.Open the application https://www.asianpaints.com/ in any browser. 2. Go to "Shop" using the redirect button below the search bar. 3.Open the 'Color Selection Tool" category. | To validate if a user can type the number for "Quantity" in checkout page | 1. Open the url in browser and sign in. 2. Click on any item shown. 3.Click on "Buy now". 4. New page opens up. 5. Take the arrow to the quantity shown, select it and type a number in order to change the quantity. | https://www.asianpaints.com/online-shop/colour-selection-tools.html | 1. User can select the quantity shown using mouse arrow and cannot change the quantity by typing. 2 User can change the quantity of item at checkout page by using only the '+' and '-' buttons show adjacent to the quantity. | 1. User is able to select the quantity shown using mouse arrow and cannot change the quantity by typing. 2 User is able to change the quantity of item at checkout page by using only the '+' and '-' buttons show adjacent to the quantity. | PASS
TC_Shop2_01 | TS_Shop_03 | 1.Open the application https://www.asianpaints.com/ in any browser. 2. Go to "Shop" using the redirect button below the search bar. | To validate if user can select products from "Wall stickers" and add to cart. | 1 Open the url and sign in 2 Select the "Wall Strickers" category. 3 Select 'add to cart' button below the items. | https://www.asianpaints.com/online-shop.html | 1 All the items should be added in cart 2 The quantity of each item must be the number of times "add to cart" button was pressed for it. | 1. The items were added in the cart. 2 All the items had '1' quantity since the button was pressed only once. | PASS
TC_Shop2_02 | TS_Shop_03 | 1.Open the application https://www.asianpaints.com/ in any browser. 2. Go to "Shop" using the redirect button below the search bar. | To validate if user can select products from "Peel and stick" and then add to cart. | 1 Open the url and sign in 2 Select the "Wall Strickers" category. 3 Select 'add to cart' button below the items. | https://www.asianpaints.com/online-shop.html | 1 All the items should be added in cart 2 The quantity of each item must be the number of times "add to cart" button was pressed for it. | 1. The items were added in the cart. 2 All the items had '1' quantity since the button was pressed only once. | PASS
TC_Shop2_03 | TS_Shop_03 | 1.Open the application https://www.asianpaints.com/ in any browser. 2. Go to "Shop" using the redirect button below the search bar. | To validate if user can select products from "wallpapers" and then add to cart. | 1 Open the url and sign in 2 Select the "Wall Strickers" category. 3 Select 'add to cart' button below the items. | https://www.asianpaints.com/online-shop.html | 1 All the items should be added in cart 2 The quantity of each item must be the number of times "add to cart" button was pressed for it. | 1. The items were added in the cart. 2 All the items had '1' quantity since the button was pressed only once. | PASS
TC_Shop2_04 | TS_Shop_03 | 1.Open the application https://www.asianpaints.com/ in any browser. 2. Go to "Shop" using the redirect button below the search bar. | To validate if user can select products from "Do it yourself" and then add to cart. | 1 Open the url and sign in 2 Select the "Wall Strickers" category. 3 Select 'add to cart' button below the items. | https://www.asianpaints.com/online-shop.html | 1 All the items should be added in cart 2 The quantity of each item must be the number of times "add to cart" button was pressed for it. | 1. The items were added in the cart. 2 All the items had '1' quantity since the button was pressed only once. | PASS
TC_Shop2_05 | TS_Shop_03 | 1.Open the application https://www.asianpaints.com/ in any browser. 2. Go to "Shop" using the redirect button below the search bar. | To validate if user can select products from "Mechanized tools" and then add to cart. | 1 Open the url and sign in 2 Select the "Mechanized Tools" category. 3 Select 'add to cart' button below the items. | https://www.asianpaints.com/online-shop.html | 1 All the items should be added in cart 2 The quantity of each item must be the number of times "add to cart" button was pressed for it. | 1. The items were added in the cart. 2 All the items had '1' quantity since the button was pressed only once. | PASS
TC_Shop2_06 | TS_Shop_03 | 1.Open the application https://www.asianpaints.com/ in any browser. 2. Go to "Shop" using the redirect button below the search bar. | To validate if user can select products from "Mask and PPE" and then add to cart. | 1 Open the url and sign in 2 Select the "Mask and PPE" category. 3 Select 'add to cart' button below the items. | https://www.asianpaints.com/online-shop.html | 1 All the items should be added in cart 2 The quantity of each item must be the number of times "add to cart" button was pressed for it. | 1. The items were added in the cart. 2 All the items had '1' quantity since the button was pressed only once. | PASS
TC_Shop2_07 | TS_Shop_03 | 1.Open the application https://www.asianpaints.com/ in any browser. 2. Go to "Shop" using the redirect button below the search bar. | To validate if user can select products from "Books and Catalogues" and then add to cart. | 1 Open the url and sign in 2 Select the "Books and catalouges" category. 3 Select 'add to cart' button below the items. | https://www.asianpaints.com/online-shop.html | 1 All the items should be added in cart 2 The quantity of each item must be the number of times "add to cart" button was pressed for it. | 1. The items were added in the cart. 2 All the items had '1' quantity since the button was pressed only once. | PASS
TC_Shop2_08 | TS_Shop_03 | 1.Open the application https://www.asianpaints.com/ in any browser. 2. Go to "Shop" using the redirect button below the search bar. | To validate if user can select products from "Adhesives" and then add to cart. | 1 Open the url and sign in 2 Select the "Adhesives" category. 3 Select 'add to cart' button below the items. | https://www.asianpaints.com/online-shop.html | 1 All the items should be added in cart 2 The quantity of each item must be the number of times "add to cart" button was pressed for it. | 1. The items were added in the cart. 2 All the items had '1' quantity since the button was pressed only once. | PASS
TC_Shop3_01 | TS_Shop_04 | 1.Open the application https://www.asianpaints.com/ in any browser. 2. Go to "Shop" using the redirect button below the search bar. | To validate if user can purchase an item from "Buy now" without signing in | 1 Open the url and do not sign in 2 Select the "Shop" from the navigation button under the search bar. 3 Select a category 4 Select an item 5 Click on "buy now" button shown below description | https://www.asianpaints.com/ | 1. After clicking "buy now", Login prompt should open up asking for the users phone number. | 1 The login prompt opened up as soon as "buy now" button was clicked which asked for the users phone number for login purpose. | PASS
TC_Shop3_02 | TS_Shop_04 | 1.Open the application https://www.asianpaints.com/ in any browser. 2. Go to "Shop" using the redirect button below the search bar. | To validate if user can purchase an item from "Buy now" after signing in | 1 Open the url and sign in 2 Select the "Shop" from the navigation button under the search bar. 3 Select a category 4 Select an item 5 Click on "buy now" button shown below description | https://www.asianpaints.com/ | 1. After clicking "buy now", the page should reload and "Checkout" page should be displayed which will show the user his "shopping car" content and the net amount payable | 1 The checkout page opened up as soon as "buy now" button was clicked which displayed the users cart total content and net payable amount. | PASS
TC_Shop4_01 | TS_Shop_05 | 1.Open the application https://www.asianpaints.com/ in any browser. | To validate that cash on delivey is applicable for cart value below 5K. | 1 Open url and sign in. 2 Select items from any category and add them to cart.(ensure that cart value is below 5k.) 3 Click on "Checkout" button at the bottom in the "cart". | https://www.asianpaints.com/online-shop.html | 1 Cash on delivery option should be selectable by the user. | 1 Cash on delivery option was selectable as the value of cart was below 5K | PASS
TC_Shop4_02 | TS_Shop_05 | 1.Open the application https://www.asianpaints.com/ in any browser. | To validate that Cash on delivey is not applicable for cart value above 5K. | 1 Open url and sign in 2 Select items from any category and add them to cart(ensure that cart value is above 5K). 3 Click on "checkout" button at the bottom in the "cart". | https://www.asianpaints.com/online-shop.html | 1 Cash on delivery option should not be selectable by the user. | 1 Cash on delivery option was not selectible as the value of the cart was above 5K. | PASS
TC_Shop4_03 | TS_Shop_05 | 1.Open the application https://www.asianpaints.com/ in any browser. | To verify that promocode shown are applicable for cash on delivery | 1 Open url and sign in 2 Add few items to the cart from any category(ensure that cart value is below 5K). 3 Click on "checkout" button at the bottom in the "cart" 4 In the payment page , use any one applicable promocode | https://www.asianpaints.com/online-shop.html | 1 User should be able to use the applicable promocode and see the amount difference in the net payable. | 1 User was able to apply code ("FESTIVESALE") and the discount in the amount was shown in the net payable. | PASS
TC_Shop5_01 | TS_Shop_06 | 1.Open the application https://www.asianpaints.com/ in any browser. | To validate we have online payment option if the cart value is below 5000 (5K). | 1 Open url and sign in. 2 Select items from any category and add them to cart.(ensure that cart value is below 5k.) 3 Click on "Checkout" button at the bottom in the "cart". | https://www.asianpaints.com/online-shop.html | 1 User should be able to select online payment option | 1 Online payment option is selectable and working. | PASS
TC_Shop5_02 | TS_Shop_06 | 1.Open the application https://www.asianpaints.com/ in any browser. | To validate we have online payment option if the cart value is above 5000 (5K). | 1 Open url and sign in 2 Select items from any category and add them to cart(ensure that cart value is above 5K). 3 Click on "checkout" button at the bottom in the "cart". | https://www.asianpaints.com/online-shop.html | 1 User should be able to select online payment option | 1 Online payment option is selectable and working. | PASS
TC_Shop5_03 | TS_Shop_06 | 1.Open the application https://www.asianpaints.com/ in any browser. | To validate that online payment is available when buying items after adding them to cart | 1 Open url and sign in 2 Select items from any category and add them to cart 3 Click on "checkout" button at the bottom in the "cart". | https://www.asianpaints.com/online-shop.html | 1 User should be able to see and select online payment option | 1 Online payment options lis selectable and working | PASS
TC_Shop5_04 | TS_Shop_06 | 1.Open the application https://www.asianpaints.com/ in any browser. | To verify that most of the online payment methods are available. | 1 Open url and sign in 2 Select items from any category and add them to cart 3 Click on "checkout" button at the bottom in the "cart". | https://www.asianpaints.com/online-shop.html | 1 User should be able to see and select from any of the online payment options. | 1 Online payment options like EMI, Credit/debit car, UPI, scan and pay,etc are shown and user selectable. | PASS
TC_Shop6_01 | TS_Shop_07 | 1.Open the application https://www.asianpaints.com/ in any browser. | To validate the functioning of pincode bar within the category section. | 1 Open url and sign in 2 Select any category 3 Click on edit button to fill the values in pincode bar | https://www.asianpaints.com/online-shop.html | 1 Pincode should be checked and a error message should be displayed making the user enter only correct values 2 User should not be allowed to enter any non numeric values and more than 6 characters. | 1 Upon entering non existing pincode value like 000000, the system accepted it and designated it as a pincode of the user. 2 User is able to enter any type of value they want and they are able to enter more than 6 values. | FAIL
TC_Shop6_02 | TS_Shop_07 | 1.Open the application https://www.asianpaints.com/ in any browser. | To validate the functioning of pincode bar within the items section. | 1 Open url and sign in 2 Select any category 3 Select a product 4 Type in the pincode in the respective bar | https://www.asianpaints.com/online-shop.html | 1 Pincode should be checked and the user should be informed whether the pincode is servicable or not. | 1 The bar only allows the user to enter numeric values 2 User is not allowed to enter more than 6 characters 3 Appropriate error messages are shown depending upon the type of error. | PASS
TC_Shop7_01 | TS_Shop_08 | 1.Open the application https://www.asianpaints.com/ in any browser. | To validate that all the items under "Shop" are searchable | 1 Open url and sign in 2 Type in items name and click on search | https://www.asianpaints.com/ | 1 The items containing keywords are displayed one below the other | 1 The items are shown in a list. 2 Al the displayed items have the respective keywords | PASS
TC_Shop8_01 | TS_Shop_09 | 1.Open the application https://www.asianpaints.com/ in any browser. | To validate that slide images are displayed and are sliding | 1 Open url and sign in 2 Wait on the "Shop" screen | https://www.asianpaints.com/online-shop.html | 1 The images should keep sliding after a defined interval 2 All the slides should have and image | 1 The images kept sliding after 5 seconds 2 Slide 5 image is not being dispalyed | FAIL
TC_Shop8_02 | TS_Shop_09 | 1.Open the application https://www.asianpaints.com/ in any browser. | To validate that slider images are clickable | 1 Open url and sign in 2 Click on the sliding image shown | https://www.asianpaints.com/online-shop.html | 1 Each image should redirect you to their resoective page 2 Each image should be clickable | 1 Images in the slides 2,3 and 4 are under maintenance 2 Slide 5 is not clickable. | FAIL
TC_Shop9-01 | TS_Shop_10 | 1.Open the application https://www.asianpaints.com/ in any browser. | To validate end to end working | 1 Open url and sign in 2 Click on 'shop' under the search bar(ER-1) 3 Select "Wall Stickers" 4 Click on filters 5 Set filters(ER-2) as: SIZE- Large PRICE- 400-499 COLLECTION- Avengers 6 Set a serviceable pincode 7 Click on "Add to Cart" for the first item(ER-3) 8 Add item to wishlist by clicking on "heart icon shown on the image(ER-4) 9 Click on Shopping bag icon in extreme left corner(ER-5) 10 Click on checkout 11 Select cash on delivery on checkout page(ER-6) 12 Give a serviceable address 13 Confirm your order placement 14 Sign out of the account from the "Profile" icon in the header | https://www.asianpaints.com/ | ER-1: User should be redirected to shop page ER-2 : User should be able to select the required filters ER-3: "Add to cart" button should work for that item ER-4: The item should reflect in the wishlist which is accessible from the heart icon in top left ER-5: The shopping bag should have the selected product and only one quantity of it ER-6: Cash on Delivery option should be selectable by the user in the checkout page | 1 User is redirected to shop page 2 User is able to select the required filters 3 "Add to cart" button is also working for that item 4 The item added to wishlist is shown in the wishlist. 5 The shopping bag has selected item in it 6 Cash on delivery option was selectable since the cart value is below 5K. | PASS

## Sprint 1
Functional Testing Case Study - 1
Task/Scenario Given: |  | The following website is given for Manual Testing to follow Agile practices and design and execute Test Cases and create Defect Report https://www.asianpaints.com/ Module:Paints & Textures, Wall Coverings, Shop
Sprint Day | Sprint Activity | Overview and scope of functionality
Sprint Day 1 | Project Management Activity: Product Owner 1. Create user stories based open functionality I. Understanding requirements II. Assign priority III. Assign user stories to team members 2. Identify the De+B3pendacy between the requirement 3. Final ordering of product backlog item( set of all user stories) Create Task / Deliverables: 1. List of User Stories & Functions to test 2. All tasks with JIRA should be ready in SCRUM template | Project Overview: Asian Paints application is intended for users to search for different Paints and colors, Textures and Wall Coverings to paint their house, office etc. The user can search for different colors, wallpapers and can shop for it. The user can even view and book a contractor based on their locality by entering pin code. In scope Functionality: Asian Paints application provides following functionalities to the end user : 1. Home Page : a. Validate the headers, Top Menu, page title and information present on the page. b. User can login through Mobile number. 2. Paints & Textures Tab: a. Verify all the colors and textures available for exterior,interiors and water proofing ,wood & metal b.User can calculate its budget required for painting from "Paint Budget calculator". c. User can get the contractor contact details in his locality through "Contractor Finder". 3. Ideas: a. User can get suggestion\ideas for its paintaing requirements. b. User can request for a free site evaluation by an Asian Paints Safe Painting Service expert. c. Select Hotel for booking 4. Shop: a. User can select\search for different wallstickers, wall papers as per their requirement. b. User can purchase a color selection tool for choosing its own color. c. User can select a product\variants and can "add it to cart" or can "buy now". d. User successfully purchased a product by Online payments\Cash on delivery option. 5. View orders: a. USer can view its own profile from "My Profile Icon". b. User can view its ordered items details in "My Order" tab. c. User sign out to verify that his profiles and ordered items are no more displayed. Out of Scope Functionality: 1. Services (Assume that due to covid 19 they have stopped this services and is going to start with online services in the next beta release. Expected Implementations : 1. Usage of all Testing Types 2. Usage of Test Design Techniques like EP, BVA etc. 3. Usage of Valid invalid input data 4. Test case design in Integration and system level testing QA Suggestions:- 1) Localization Testing most important 2) Exchange Rate (That Means Gobal Currency values should show correctly as per selected currency) 3) UI Testing 4) Scenario based Testing such as basic, alternate etc.
Sprint Day 2 | JIRA Task and Test Design : Dev Team 1. Assign story point or time required to accomplish the story/Task 2. Categorize user stories in to Epic, User Stories, Tasks & SubTasks 3. Assign the stories to components 4. Add group members in th Project on JIRA. 5. Create MAnual Test Scenarios Create Task / Deliverables: 1. Test scenarios 2. Test Case design
Sprint Day 3 | Scrum Team activities : Dev Team 1. Create scrum based sprints 2. Create Sprint backlog (select the stories for the particular Sprint) 3. Create Sprint board (Todo , in process, Done) Create Task / Deliverables: 1. Test Case design 2. Test Case execution
Sprint Day 4 | Scrum Team Activity : Scrum Team (PO, SM, DT) 1. Plan for release 2. Generate Agile report relevant to scrum project (e.g. Burn down chart, Sprint report etc.) Create Task / Deliverables: 1. Defect reporting 2. Traceability Matrix 3. Test summary report
Sprint Day 5 | Sprint Evaluation

## Who is going to take what
Name | Module
Sakshi Jamanani | Home Page
Ananth D | Ideas & View Orders
Yogesh | Paints & Textures
Divyansh Singh | Shop

## Ideas
Issue Type | Summary | Priority
Epic 1 | Idea functionality
Story 1 | As a user, I want to view the different options/styles used so that I can choose from a variety of styles | P1
Story 2 | As a user, I want to fill the enquiry form so that I can avail a free site evaluation visit | P2 | Does the bot message you immediately or not | Does the document "The color book AP" open immediately upon clicking the submit button
Story 3 | As a user, I should be able to filter from the choice of products shown based on my preferences | P3

## View Orders
Issue Type | Issue Type | Priority
Epic 1 | User's Profile
Story 1 | As a user, I want to view my profile so that I can edit my personal details | P3
Story 2 | As a user, I want to view my past/current orders on Asian Paints so that I can gather information about the same | P2
Story 3 | As a user I want to view my bills, so that I can view them at any point of time | P4
Epic 2 | Sign-out Functionality
Story 1 | As a user, I should be able to Sign-out of my account successfully | P1